## Sheet1
Pos. | Location | Location description or East/West boundaries | Notes | Aspirational VM Priority (from AJ notes) 1-3 | Identified for priority maintenance Y/N | Identified for 14 day mooring improvements (inexpensive bank work maintenance) Y/N | Identified as having Car Parking improvement potential Y/N | Location dropped - deemed not appropriate for any changes | Dale's notes from Site Visits
0 | Lock 44 to Lock 50 |  | Not much room between lock 44 and 50 for fishing due to amount of boats. Also affects moorings for other boat users. Facilitate meeting to discuss . DM
1 | Lock 50 to Cemetery Bridge |  | Currently 72 hours on towpath side.To be trialled at 72 hours.Due to the re-development plans for the offside of Devizes Wharf there is no guarantee that the 48 hour visitor moorings on the offside will remain visitor moorings. | N/A | N | N | N | N
2 | Cemetery Bridge to Park Road Bridge |  | Aspirational works to be carried out to make this stretch moorable for 14 days then change Devizes Wharf towpath side to 48hrs. | 2 | Y - volunteers to make better access to canal edge to towpath. Underwater obstructrions in this length, Inspection needed either by dewatering or using the grab boat | Y | N | N | Raise ZX for Chew Valley to grab debris from this area, when next passing. AJ
3 | Devizes Marina & Hourglass Public House |  | Group agreed to leave as is – but to encourage the Hourglass to improve the pub moorings to make them more attractive/easier to moor and promote them. Group to contact Marstons - can CRT help them improve the moorings? | N/A | Y | Y | N | N
4 | Horton Bridge |  | Aspiration to bring up to standard for visitor moorings. Consider towpath upgrade - due to the public house and potential visitors. Review the length of the 48-hour moorings here.NB there is also a 24 hour mooring of approx 5 boat lengths west of the bridge on the offside below the pub that is managed by the pub.The group suggested leaving moorings at 48 hours with an aspiration to improve the visitor moorings. | 3 | N | N | N | N
5 | Bishops Cannings swing bridge |  | Winding hole to bridge could be used as visitor moorings, as a public footpath from there to local facilities in Bishops Cannings. CR to approach Pubs for signs on canalside. | 3 | Y - Requires no bank maintenance but needs red posts. | y | N | N
6 | Allington Swing Bridge |  | Winding hole to bridge could be used as informal visitor moorings, as a public footpath from there to local facilities in All Cannings.However if day hire boaters need to turn at the winding hole the VMs need to be west of the winding hole ie not between the bridge and winding hole. Could be an Aspiration 1 or 2. It's a 1 if the Barge Inn doesnt re-open and or if engineers assess leaks in bank as requiring action. | 1 | Put on stakeholders agenda to install hard edge VM's between SB and Winding Hole, and to the West of winding hole. Total of 200m | y | N | N | Raise Zx for the Install of Informal moorings. AJ
7 | All Cannings |  | Shortage of 48-hour visitor moorings in this area. There is a potential to increase the visitor mooring length to the East. Would mean extending the piled section. Dredging would be required to improve 14-day moorings. This item is only a priority 3, as item 6 is a priority 1. | 3 | N | Y | Carpark surface needs improving with Tarmac. Opportunity to take road planings from WCC to resurface car parks. KO to put DM in contact. | N | Ken oliver to put Dale in Contact with council colleague with a view to obtaining road planings to repair towpath surface
8 | Honeystreet |  | Total length of visitor morning is 170m. 150m of it is hard bank protection of which the first section (west) is 130m long. The next 25m is for the water point, which makes up the last section of hard edge, the last 15m is not hard bank. Recommendation - Totems are changed to have the last 20 m of hard edge as water point only, leaving 150m of 48 hour mooring this would involve moving the totem on the east and changing tiles so that this section defines the water only section. Aspiration to pile the section between end of current piled section to Honeystreet rd bridge. | 3 | Y - Totems are changed to have the last 20 m of hard edge as water point only, leaving 150m of 48 hour mooring this would involve moving the totem on the east and changing tiles so that this section defines the water only section. | Y | N | N | Raise a zx for movement of the totem post
9 | Wilcot Road |  | Popular destination. Consider - 24-hour visitor moorings west of Wilcot Bridge for access to the Golden Swan which is across the village green. Improved signage for the Golden Swan required here. Additional short length area to the West for visitor moorings. This would repair the area where the bank has collapsed too. Needs to be a quiet zone. | 3 | Y - Improved signage for the Golden Swan required here. | N | yes - parish council are looking at improving surafce on lane alongside canal, some reduction in parking in planned. | N
10 | Pewsey |  | Visitor moorings ok at this destination, leave as it is. | N/A | N | N | N | Y
11 | Wootton Rivers |  | Aspiration to move permanent moorings below (West) of lock to pound between lock 51 & 52. and turn former permanent moorings below the lock into 48-hour visitor moorings. Changes to be carried out winter 18/19 once gates have be relined. On completion of works, install signage asking craft to turn here if not travelling any further east. | 1 | N | N | Village Hall car park used and 4/5 bays neabry and 2/3 space on south side. Possible conflict with the church. Suggestion is that 12 hours max parking put on these space - CRT to ask landowner | N | At the recent stakeholders meeting it was discussed that re lining top and bottom gates at Lock 51 this has been included in the winter works 2018/19
12 | Cadley Lock |  | Extra-long landing stage above lock, consider using the end section as 48hr mooring. The landing stage above Cadley lock is 41m long. This could be marked up as 25m Lock landing, leaving 16m of hard edge which could be used as Visitor moorings, albeit a bit short and could make it difficult for craft to get on and off the lock landing. Recommendation – Install a Totem between the 5th and 6th bollard signing lock landing to the right and 48hr VM to the left. A decision needs to be made as to how long this 48hr VM would be given only 16m is hard edge. | N/A | N | N | N | Y
13 | Bruce Tunnel West |  | Towpath is disappearing West of the tunnel. Aspiration for visitor moorings with a hard edge either side of the tunnel. Bank Collapsiing here, engineers to assess. | 2 | Y - Bank Collapsiing here, engineers to assess. | N | N | N | Raise a ZX for the repair of the collapsing bank. Put on Engineers work centre. AJ
14 | Crofton |  | Leave as 48 hours as a visitor attraction. | N/A | N | N | N | Y
15 | Mill Road Bridge |  | Leave as is | N/A | N | N | N | Y
16 | Great Bedwyn |  | A common turning point for day or short-term boat hirers. Aspiration for visitor moorings above Church Lock for a hard edge visitor mooring (48 hours). | 1 | N | N | N | N | Raise at the next stakeholders meeting. Ask engineers to put in future business plan. - More likely to be in B20 /B21
17 | Lock 70 - 71 (was Froxfeild) |  | 2 boat lengths required for 48-hour mooring. is also a cheap gain for visitor moorings as it only requires totems. Improvements to the towpath / bank west of lock 68 to make better 14 day section, would mitigate the loss of 14 day moorings here. | 1 | Y - only requires totems | N | N | N | Raise ZX for install of two totem poles. AJ
18 | Hungerford |  | The group discussed the lack of suitable moorings in the Hungerford area. The 48-hour mornings between Hungerford lock and Hungerford Town Bridge are not up to standard It was proposed to pile this section. Aspiration to install between 100 and 200 m of hard edge moorings east of Everlands Road Bridge. Horse boat requires consideration when making improvements in the Hungerford area. Hungerford Town and Manor often raise complaints about boating activities in the Hungerford area -particularly in relation to the vehicles that arrive with these boats, as well as poor parking and general over staying they may well object to the installation of further moorings in the Hungerford area. Upgrade and hard edge the section between Hungerford church swing bridge and Hungerford Marsh lock (to the gateway onto the Marsh). | 1 | Y - Totems in the winding hole | N | N | N | Raised at Stakeholders meeting
19 | Dunmill |  | No issues. | N/A | N | N | N | Y
20 | Wire Lock |  | A bit shallow in places. The area between Wire Lock and kintbury should have an informal mooring section. Due to issues with horse boat, no informal moorings. | N/A | N | N | N | Y
21 | Kintbury |  | A bigger gap should be left for the water point at Kintbury, suggestion that we paint a yellow line along the fender marking out the waterpoint only section. Due to issues with horse boat, no informal moorings. | N/A | Y - Paint a yellow line along the fender marking out the waterpoint only section. | N | N | N | Raise a zx for painting of yellow lines. Put on KAVO. AJ
21.5 | Kintbury - Water points in general. |  | 35 ft. is required either side of all water points to enable 70 ft. craft to get onto the point Signage/markers required either side of water point to mark up the water. Moorings in the Kintbury area need to be kept to a minimum to ensure the horse boat is able to continue their business. The horse boat is beneficial to the Kennet and Avon Canal. Signage required at dreweatts lock for the horse boat. | N/A | Y - Signage/markers required either side of water point to mark up the water. Signage required at dreweatts lock for the horse boat. | N | N | N | Raise a zx for the install of two totems either side of water point. Put on KAVO. AJ
22 | Brunsden |  | The tow path in this area has recently been resurfaced, and bank protection work has been carried out here. Due to issues with horse boat, no informal moorings. | N/A | N | N | N | Y
23 | Dreweatts Lock |  | Aspiration to have informal moorings above the lock, off the end of the landing stage There are issues in this area with offside vegetation. Due to issues with horse boat, no informal moorings. | N/A | N | N | N | N | Signage required at Dreweatts lock for Horse boat. Raise a ZX . AJ
24 | Hampstead Lock |  | There is a lack of moorings at Hampstead Lock. Aspiration to have 100 m of 48-hour moorings above the lock with rings/ bollards. Contingent on making below the lock usable as 14 day mooring. Aspiration for an informal moorings section between 50 and 100 m below Hampstead Road Bridge. It was noted that Pamela Smith would prefer this area to remain 14 days. Dale to identify where the informal mooring sections are located | 1 | Y - Clearing 100m below lock for 14 day mooring with volunteer boat | Y | N | N | Lock landing is in good condition. Then we have a 72 foot winding hole. We then have two boats moored up on the 14 day stretch. No problems after winding hole with the next section all the way along being a 14 day morning Plenty of width here. Option to put in some posts to make this section an informal mooring site. Above the lock, the current layout is a 25m Landing stage, 100m of Nicospan bank protection, which fiunishes 100mm below waterline (during today's vist) then 60m of normal towpath bank, before winding hole, which is where the river splits. Therefore realistically there is a 60m section that could be improved to make a 48hr mooring hard edge. There were plenty of craft moored against the Nicospan protected towpath bank, but boards needed to reach towpath. Local land owner has requested that this area is marked as a no winding hole due to siltation / sandbar issues which is damaging their fishery.Proposal to remove winding hole and install one below the lock. Actions; No lock landing only sign below lock. Need to order and erect one. Raise a ZX and order sign. AJ Raise a ZX for clearing 100m of vegetation from volunteer workboat, put on KAVO. AJ Raise a ZX for the removal of winding hole totem post from above lock and reinstall below lock. AJ
25 | Benham Lock |  | Aspiration to have a mooring above Benham lock, off end of lock landing, this is a nice quiet remote mooring spot. | 1 | Y - Cut out 14 day informal moorings, and mark them up with red posts. | Y | N | N | Raise a ZX for the install of informal moorings here. AJ
26 | Higgs Lock |  | A noisy area, not particularly popular as next to the A34 flyover. | N/A | N | N | N | Y
27 | Guyers Lock |  | Bank protection has recently taken place here and the vegetation has been cut to improve the bank, no particular issues | N/A | N | N | N | Y
28 | West Mills |  | Change all 24-hour moorings tiles to 48-hour moorings. Ali to raise a ZX AJ | N/A | Y - Change all 24-hour moorings tiles to 48-hour moorings. | Y | N | N | Raise a ZX for the changing of the 24hr tiles to 48hr tiles. AJ
29 | Victoria Park |  | Suggestion that additional mooring rings be installed following the success of the floating market. The group generally disagreed with this suggestion. | N/A | ? | N | N | ?
30 | Bulls Swingbridge |  | Aspiration to have informal moorings to the west of Bull’s Swingbridge. Complaints received from Fishing club this week of too many craft mooring in this section and not leaving gaps for fishing. Potential for Water Point here between S/Bridge and lock. DM has put in an application for funding. | N/A | Y - Cut out 14 day informal moorings, and mark them up with red posts. | Y | N | N | Application with drawn because Operational Buildings have a 60 k budget to installcustomer service facilities at Newbury Wharf. Raise a zx for install of Informal moorings. AJ
31 | Widmead Lock |  | Aspiration to have informal moorings on the towpath above Widmead lock. | N/A | Y - mark informal moorings on offside above lock with red posts. | y | N | N | Mark out informal moorings on offisde above the lock. Raise a ZX. AJ
32 | Monkey Marsh |  | Proposal to extend 48-hour moorings by 25m west of Thatcham Road Bridge to the mouth of the river? Group agreed 8/3 abandon as too many engineering issues | N/A | N | N | N | Y
33 | Colthrop lock |  | No issues in this area. | N/A | N | N | N | Y
34 | Midgham lock |  | Consider installing informal moorings above Midgham lock from lock landing to the bend in the Canal. | N/A | Y - Vegetation Management / cut out 14 day informal moorings, and mark them up with red posts. | Y | N | N | Raise a zx for install of Informal moorings. AJ
35 | Heales lock |  | No issues here. | N/A | N | N | N | Y
36 | Woolhampton Lock |  | Winter moorings located here above the lock, a popular spot and well used. Dale to review the signage between Woolhampton Swing bridge and lock This should be a’ no mooring’ section, with landings for lock and swing bridge use only, and signed appropriately. Landing stage to east of Swing bridge is not long enough to stop on to pick up crew due to strong flow of river. Add to stakeholder meeting , install of floating landing stage (in stock at devizes) | N/A | Y - See notes | Y | N | N | Raise a ZX For 4 signs below lock. Orderfrom Contract signs AJ 500mm x 400mm Craft navigating through lock, should open Swing bridge before leaving lock and proceed straight through the bridge and moor up on landing stage. Raise ZX for 4 signs and order them contract signs. AJ (Will go between the bridge and Lock) 500mm x 400mm Mooring for Emergency operation of Lock and bridge only. No overnight mooring Raise a ZX for 2 signs above lock. Order from Contract signs. AJ 500mm x 400mm Mooring for lock operation only. Craft navigating through lock, should open Swing bridge before leaving lock and proceed straight through the bridge and moor up on landing stage. Landing stage below (East) of swingbridge needs to be longer due to strong flows and difficulty in stopping quickly to pick up crew. Raise a ZX for moving of landing stage signage to increase length. AJ
37 | Frouds Bridge |  | downstream of the Junction of Froud’s Marina on towpath side to be considered as an informal mooring location. Offside requires cutting back to allow for wide beam moorings. A comprehensive offside vegetation cut is required. The trust may not own this section. DM to visit. and check on veg clearance progress | N/A | Y - Offside requires cutting back to allow for wide beam moorings. | Y | N | N | Raise Zx for offisde veg management in this area. AJ Raise ZX for install of informal Moorings. AJ
38 | Aldermaston | below lift bridge down to lock | Not enough visitor moorings at Aldermaston. Aspiration to improve towpath bank above Aldermaston Lock, this is not currently a visitor mooring. The trees need cutting on the off side in this section to allow space for wide beam craft to moor. | N/A | Y - The trees need cutting on the off side in this section to allow space for wide beam craft to moor. Cut and red posts. | Y | N | N
39 | Aldermaston wharf |  | Aspiration for the whole section below the swing bridge to be half visitor moorings and half 14-day moorings This section should not revert to managed moorings. Pamela Smith reports that the towpath and bank below Padworth lock is not in very good condition and requires improvement. ZX's are on the system for this. This has been noted in a separate towpath condition survey meeting. Dependant on what happens with redevelopment of the wharf in future. DM to check ownership of the towpath between end of ABC's site to the liftbridge. | N/A | Y - check that a "facility mooring" sign is still there for water/sanitary | N | N | N | Dm reports that the Trusst owns the towpath.
40 | Towney Lock |  | Dale made the group aware of the network rail proposal to close the crossing point adjacent to Towney lock, as part of the electrification of the railway project. | N/A | N | N | N | Y
41 | Ufton |  | Ideal area for an informal mooring spot. (River section below Ufton Swing bridge) | N/A | Y - Cut out 14 day informal moorings, and mark them up with red posts. Very long length - DM to assess red post plan. | Y |  | N | Raise a zx for install of Informal moorings. AJ
42 | Tyle Mill |  | The last two mooring spots on the end of the permanent mooring section above Tyle Mill need signage installed to change them to 48-hour section. Totems will need installing, Ali to raise a zx. DM to action. Check standard of landing stages are approriate for VM usage. | 1 | Y - The last two mooring spots on the end of the permanent mooring section above Tyle Mill need signage installed to change them to 48-hour section. | N | N | N | Raise Zx for The last two mooring spots on the end of the permanent mooring section above Tyle Mill. Install 2 Totems signage and mark as 48-hour section. AJ
43 | Sulhamstead lock |  | No issues. | N/A | N | N | N | Y | Totems will need installing, Ali to raise a zx. DM to action.
44 | Sheffield to Garston lock |  | Informal morning section required in this area. 8/3 group ideantified area as not viable. | N/A | N | N | N | Y | Craft navigating through bridge, should open bottom gates of lock first and proceed through bridge and straight into the lock.
45 | Hisseys Bridge |  | Issues with motorbikes on towpath in this area. The trust does not own the bank here and the tow path is just the edge of a field, not a suitable area for mooring. 8/3 group identified area as not viable. | N/A | N | N | N | Y
46 | Burghfield |  | There is very low free board in the section between Burghfield Road Bridge and Burghfield Lock. The towpath is regularly overtopped in this area. This section is the first suitable area to moor when travelling west from Reading, and a 48-hour mooring section for craft is required. Hard edge and towpath improvements will be required. The towpath bank will need raising and improving. Both sides of Burghfield Road Bridge- Signage will be required to alert boaters to the risk of flooding. Remove old wooden landing stage to the rear of the cunning man pub. East of Burghfield bridge aspirational three boat length mooring for safety reasons (river flooding). | 1 | Y - Remove old wooden landing stage to the rear of the cunning man pub. | N | N | Y | We need 2 signs above lock.
47 | Southcote Lock |  | A nice spot to moor but very narrow and not suitable for wide beam craft. | N/A | N | N | N | Y | 500mm x 400mm
48 | Fobney Lock |  | Not encouraging any craft to moor in this area due to anti-social issues. | N/A | N | N | N | Y | Mooring for lock operation only.
49 | County Lock |  | No moorings in this section due to strong stream flows. Moorings to the east of the Oracle shopping centre, some bollards here for visitors. Pamela Smith reports that there is a water tap in the bush at the end of the landing stage east of the Oracle, she asked whether this could be turned into a trust water point and rubbish point. Dale to investigate. Mark to consult with Reading Borough Council re-the charges they are making to boaters wishing to more on the section to the east of the Oracle. Establish whether the craft have a right to moor in this section for a reasonable time and to establish what Reading Borough Council's plans are for this area List of informal morning locations to go into the Urbis boards. | N/A | Y - See notes | N | N | N | This tap is abandoned and not on trust property. Belongs to EA we believe
50
51